**GDF Project Report – Sprint 3**

**Group Members:**

|  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| |  |  | | --- | --- | | Ihsan Salman Jasim |  | | Shaymaa Alhayali |  | | Hala Fathee |  | | Hadeel Tariq |  | | Tareq Abed Mohammed |  | |  |
|  |  |
|  |  |

**Description:**

GDF (General Discussion Forum) is a Web-based application for general information, which enables users to view a list of variant topics and search these topics with keywords . The user can also open a new discussion topic, add comments and give rating to other comments.

**Product Backlog:**

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **ID** | **Story** | **Priority** | **Time Estimation** | **Status** |
| 1- | View the list of system contents in general. | 1 | 3 days | Completed |
| 2- | The customer can search topics with keywords. | 3 | 2 days | In progress |
| 3- | The customer needs to see the date and time of comments. | 3 | 3 days | Completed |
| 4- | The customer can add comment in a selected discussion topics(inside topic page). | 5 | 3 days | Not started |
| 5- | Customer can give a rating to others comments | 5 | 3 days | Not started |
| 6- | View some advertisement pictures | 1 | 2 days | Completed |
| 7- | The administrator can add new topics | 4 | 2 days | Not started |
| 8- | The customer can suggest a new topic area. | 3 | 2 days | In progress |
| 9- | Give the customer a permission to object on some topic area . | 5 | 2 days | Not started |
| 10- | Give the customer the ability to uploading some resources(books, pictures). | 4 | 3 days | Not started |
| 11- | The customer can register him/her self | 2 | 2 days | In progress |
| 12- | Finalizing and putting the final touches to the project | 6 | 1 day | Not started |

The marked items are selected to be completed for this Sprint.

**Sprint 3 Backlog:**

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **ID** | **Task** | **Responsible** | **Time Estimation** | **Progress** |
| 2.1 | Designing a form for searching between two specified dates. | Ihsan+Hadeel | 12 hours | Completed |
| 2.2 | The form can also search depending on a sart date. | Ihsan+Hadeel+Tareq+ Hala+Shaymaa | 6 hours | Completed |
| 2.3 | The form can start searching before the specified date. | Ihsan+Shaymaa | 8 hours | In progress |
| 2.4 | The form can be used to search in general without any specification. | Ihsan+Hadeel | 6 hours | completed |
| 2.5 | The searching form used a specified topics, subjects, body or selecting one or two of them or may be all of them. | Hadeel+Tareq+Hala+ Shaymaa | 16 hours | completed |
| 3.1 | Updating the form comment to put the date and time for each comment addition to the database. | Shaymaa+ Hala | 1 day | Completed |
| 8.1 | Design a form for customer’s suggestion related with the table in data base. | Ihsan+Hadeel+Tareq+ Hala+Shaymaa | 1 day | Completed |
| 8.2 | Designing a form for giving the ability to the adminstrator to approve or not approve the customer suggestion. | Hadeel+Tareq+Hala+ Shaymaa | 2 days | In progress |

**Burn-down Chart:**

**Accuracy of Time Estimations:**

|  |  |  |
| --- | --- | --- |
| **Product Backlog Item** | **Estimated Completion Time** | **Actual Time Spent** |
| 3 | 3 days | 1 day |